## Index
Lean Six Sigma Templates
Updated: | 2013-01-01
# | Worksheet Title
1 | DMAIC Project Milestones
2 | OARP Chart
3 | Project Charter
4 | Stakeholder Analysis (basic)
5 | Communication Plan
6 | SIPOC
7 | CTQ Tree
8 | CTC/CTB/CTQ Matrix
9 | QFD
10 | Data Collection Plan
11 | Measurement System Analysis
12 | Value Adding Analysis
13 | Solution Selection Matrix
14 | FMEA
15 | Control Plan
16 | Change Sustainability Model

## DMAIC Project Milestones
DMAIC Project Milestones
Index
|  | Target | Actual | Primary Person
| Milestone (Tollgate Review Moment) | Completion | Completion | Responsible (RACI)
# | PLAN - Tollgate Review Define
1 | VOC gathered (e.g., Kano questionnaire, VOC workshop)
2 | VOC/VOB translated to CTC/CTB/CTQ Requirement(s)
3 | First draft of Charter completed (incl. BuCa & Performance Goal)
4 | Check existing best practices (before starting this DMAIC)
5 | Stakeholder Analysis completed
6 | Communication plan created
7 | Team established
8 | Initial team formation meeting held
9 | Project scoped to manageable size
10 | Project 'y' metric determined (Process Indicator determined)
11 | SIPOC map (or process flow scheme) completed
12 | Agreed version of Charter completed
PLAN - Tollgate Review Measure
13 | Operational Definition 'y' metric completed
14 | List of Potential X's brainstormed (e.g., fishbone, VSM draft)
15 | Data Collection Plan developed
16 | Measurement System Analysis performed
17 | Baseline (current process performance) determined
18 | Performance goal (re)established
19 | Charter, stakeholder analysis updated
20 | Potential Quick Wins identified
21 | Story board update (DMAIC)
DEVELOP - Tollgate Review Analyse
22 | Detailed Process Map created
23 | Value-Added Flow Analysis and/or other 'streamlining' performed
24 | Graphs & statistics used to stratify data
25 | Failure Modes identified using an FMEA (optional)
26 | Y-X relationship verified using graphs/ Hyp. Testing/ experiments
27 | Deepened understanding of causes (e.g., using fishbones/ 5*Why)
28 | Impact of the Root Causes (key X's) verified
29
30 | Charter updated
31 | Story board update (DMAIC)
DEVELOP - Tollgate Review Improve
32 | Possible solutions generated
33 | Possible Solutions selected & agreed upon
34 | FMEA performed on possible implementation risks
35 | Measurement System Analysis performed on Vital X's
36 | Tolerances on vital X's determined/ Overview of the new standard
37 | Implementation Plan delivered
38 | Pilot performed (optional)
39 | Performance of 'y' optimized / Improved
40 | Project status communicated to stakeholders (DMAIC)
OPERATE - Tollgate Review Control
41 | Control plan developed/implemented
42 | New performance of 'y' verified (both statistically & financially)
43 | Monitoring/tracking of y and Vital x's in place
44 | Project documentation completed (included a A4 1-pager)
45 | Start of Lean Operational Management initiative
46 | Sign-offs/official closure complete
47 | Project results communicated as per communication plan

## OARP Chart - DMAIC Overview
OARP Chart
Index
| Task/Decision/Objective (What) |  | Team / Indvidual | Team/ Individual 1 | Team/ Individual 2 | Team/ Individual 3 | Team/ Individual 4 | Team/ Individual 5
# | PLAN - Tollgate Review Define | Target Date | Actual Date | [5 empty] | Codes:
1 | VOC gathered (e.g., Kano questionnaire, VOC workshop) | [7 empty] | O = Owner
2 | VOC/VOB translated to CTC/CTB/CTQ Requirement(s) | [7 empty] | A = Approver
3 | First draft of Charter completed (incl. BuCa & Performance Goal) | [7 empty] | R = Reviewer
4 | Check existing best practices (before starting this DMAIC)
5 | Stakeholder Analysis completed | [7 empty] | P = Participant
6 | Communication plan created
7 | Team established
8 | Initial team formation meeting held
9 | Project scoped to manageable size
10 | Project 'y' metric determined (Process Indicator determined)
11 | SIPOC map (or process flow scheme) completed
12 | Agreed version of Charter completed
PLAN - Tollgate Review Measure
13 | Operational Definition 'y' metric completed
14 | List of Potential X's brainstormed (e.g., fishbone, VSM draft)
15 | Data Collection Plan developed
16 | Measurement System Analysis performed
17 | Baseline (current process performance) determined
18 | Performance goal (re)established
19 | Charter, stakeholder analysis updated
20 | Potential Quick Wins identified
21 | Story board update (DMAIC)
DEVELOP - Tollgate Review Analyse
22 | Detailed Process Map created
23 | Value-Added Flow Analysis and/or other 'streamlining' performed
24 | Graphs & statistics used to stratify data
25 | Failure Modes identified using an FMEA (optional)
26 | Y-X relationship verified using graphs/ Hyp. Testing/ experiments
27 | Deepened understanding of causes (e.g., using fishbones/ 5*Why)
28 | Impact of the Root Causes (key X's) verified
29
30 | Charter updated
31 | Story board update (DMAIC)
DEVELOP - Tollgate Review Improve
32 | Possible solutions generated
33 | Possible Solutions selected & agreed upon
34 | FMEA performed on possible implementation risks
35 | Measurement System Analysis performed on Vital X's
36 | Tolerances on vital X's determined/ Overview of the new standard
37 | Implementation Plan delivered
38 | Pilot performed (optional)
39 | Performance of 'y' optimized / Improved
40 | Project status communicated to stakeholders (DMAIC)
OPERATE - Tollgate Review Control
41 | Control plan developed/implemented
42 | New performance of 'y' verified (both statistically & financially)
43 | Monitoring/tracking of y and Vital x's in place
44 | Project documentation completed (included a A4 1-pager)
45 | Start of Lean Operational Management initiative
46 | Sign-offs/official closure complete
47 | Project results communicated as per communication plan
NOTE: The template contains a SAMPLE of potential tasks for an OARP Chart. Please enter the tasks appropriate to your project needs.

## Project Charter
Project Charter
Index
Project Charter
Project Title:
Date (1st draft):
Date (last version):
GB/BB (in training):
1. Problem Statement |  |  |  | 2. Goal Statement
Problem statement: (Problem in one sentence: in process/department xx the performance yy is below target) Clarification: (clarify why this is a relevant problem for the organisation: "what will happen if this problem is not being addressed", f.i. impact on customers, cost, marketshare, etc.) |  |  |  | (make it SMART, starting-point are the Voice of the Customer / Voice of the Business criteria)
3. Scoping |  |  |  | 4. Business Case
In Scope: |  |  |  | Hard (financial) benefits
Out of Scope: |  |  |  | Soft benefits:
5. Project planning |  |  |  | 6. Team:
Phase planning | Start Date | Review Date | Actual End | Name: | Role: | Effort (% FTE):
Define
Measure |  |  |  | YOU the Belt | GB/ PL | 40
Analyze |  |  |  | Specialist 1 |  | 10
Improve |  |  |  | Operator 1 |  | 10
Control
Signature Project Leader (Belt) |  |  |  | Signature Process Owner
Signature Sponsor

## Stakeholder Analysis (basic)
Stakeholder Analysis (basic)
Index
Primary Stakeholders (people or organizations who can affect the change, or who will be affected)
Level of Commitment | Person/Org | Person/Org | Person/Org | Person/Org | Person/Org | Person/Org | Person/Org | Person/Org | Person/Org
eg | Xl | Xl | Xl
Help it Work - will lend appropriate support |  |  |  | l |  | l | l | l
Hesitant - holds some reservations; will not volunteer |  |  |  |  | l |  | X
Indifferent - will not help, will not hurt |  |  |  |  | X | X |  |  | l
Uncooperative - will have to be prodded |  |  |  | X |  |  |  |  | X
Opposed - will openly act on and state opposition | [7 empty] | X
Hostile - will block at all costs
Not Yet Informed - involve when appropriate
X = where they are |  | - | Does everyone need to be Strongly Supportive?
l = where we want them to be |  | - | Does everyone need to move up?
|  | - | How do we get them where we want them to be?
NOTE: This template contains SAMPLE data. Please enter names and symbols according to according to your project needs.

## Communication Plan
Communication Plan
Index
Event | Timing | Audience | High Level Messaging & Key Elements | Sender | Communication Vehicle | Content Creator | Status

## SIPOC
SIPOC
Index
Process Start: |  |  | Process End:
Suppliers | Inputs (X) | Process Steps | Outputs | Customers
1 | 1 |  | 1 | 1
2 | 2 |  | 2 | 2
3 | 3 |  | 3 | 3
13

## CTC-CTQ Tree
CTQ Tree Diagram
Index
| Company Y's | Big Y's /(dis)satisfiers | Little y's | CTQ's/ CTC Requirements
| 1. @ Strategic company level, such as Customer Satisfcation (CS), CI maturity, etc. | 2. Global metric @ business and local (unit) level | 3. Performance Measurements @ tactical, internal program/process performance level | 4. Measurable requirements per Value Stream, Process, product cycle, production flow or family of products
Experience Outcomes Satisfaction, Value / Recommend / Repurchase |  | Faster | Reduce Cycle Time | Cycle time of Service Y should not be longer than 5 working days because customers need them ususally within a week
|  |  | Reduce Repair Time | Repair time of Service Y should not be longer than 1 working day, because otherwise the customer has planning issues and it is costing us a fine (contractual agreement X)
| CS | Better | Reduce Defects
Reduce Rework
|  | Cheaper | Reduce Cost of Failure

## CTC-CTB-CTQ Matrix
CTC-CTB Matrix
Index
VOC feedback (Voice of the Customer) | Key issue feedback | CTC Requirement(s) (Critical To Customer)
I do not have access to the Excel template! Can't access the Y-directory. I have to wait. | Availability | 99% uptime of the L6S toolbox on the Y-schijf
Y-directory too much out of service
Too much downtime
VOB feedback (Voice of the Business) | Key issue feedback | CTB Requirement(s) (Critical To Business)

## QFD
QFD (simplified first matrix house)
Index
|  | Importance | y1 | y2 | y3 | y4 | y5 | y6 | y7 | y8 | y9 | Competition
| CTQ#1 | 0
| CTQ#2 | 0
| CTQ#3 | 0
| CTQ#4 | 0
| CTQ#5 | 0
| CTQ#6 | 0
| CTQ#7 | 0
| CTQ#8 | 0
| CTQ#9 | 0
| CTQ#10 | 0
|  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Measurement
Competitive Levels
1: better than
2: even with
3: poorer than
Dimensional units
for Measurement
of each y
Whats
Hows
Priority Ranking

## Data Collection Plan
Data Collection Plan
Index
Performance Measure (Y/X or I/P/O metric or indicator) | Operational Definition of the metric (1.) The start & stop & HOW of the measure procedure (2.) WHAT are both the statistical & fysical units? (3.) WHAT is (are) the CTC Requirement(s)? | Discrete or Continuous data | Data Source and Location | Sample Size | Who Will Collect the Data | When Will the Data Be Collected | How Will the Data Be Collected | Other Data that Should Be Collected at the Same Time
KPI = Lead time | Per feature. Starting point is the creation of a case in CRM (support, sales) or an email (by, e.g., Bas or third party). It ends when the customer is informed. Or… Installed. |  | CRM and email systems | 20-30 features | Rob | week 42
KPI = Number of cases | Logged case into the CRM system after release (related). |  | CRM | At least from january 2013 | Friso | week 42
Q | Number of communications about each feature |  | email systems | At least from january 2013 | Friso | week 42
Q | Types of cases & relation to the feature (Measure ratio between types of cases (pareto)) |  | CRM | At least from january 2013 | Friso | week 42
T | Number of proper planning at the start |  |  | At least from january 2013 | Rob | week 42
T | Number of case produced by the beta |  | CRM | At least from january 2013 | Friso | week 42
T | Is a feature tested? |  | FSM | At least from january 2013 | Bart-Jeroen | week 42
T | Is the test defined? |  | FSM | At least from january 2013 | Bart-Jeroen | week 42
Definition of the 'Y':
Definition of 'Opportunity':

## MSA Summary
Measurement System Analysis (MSA) Summary
Index
Metric | Possible sources of Error (5*M's) | Type of MSA method | Results of the MSA method | Improvement actions |  | Alternative data source | What is the MSA quality performance now?
Lead time of ASML incidents |  | M.b.v. eigen observaties CRM data gevalideerd. | Enkel verschillen in afronding
reject rate printed T-shirts (good/ bad) | See fishbone & CTQs dep. | Kappa method | Kappa = 0,3 | training 2 hours all | plastied definitions & coloured examples | not applicable | Kappa = 0,7 (now OK)
|  | Grafieken gebruikt om outliers / typefouten te zien | 10% data errors | 10% eruit gehaald |  | not applicable
IJkingsprocedure X gebruikt

## Value Adding Analysis
Value Adding Analysis
Index
| Process Step | Value-Adding? | Value-Enabling? | Non-Value-Adding? | Work Time | Wait Time | Total Cycle Time
1 | Customer calls order service | x |  |  | 2 |  | 2
2 | Take order | x |  |  | 6 |  | 6
3 | Enter delivery date/time | x |  |  | 1 |  | 1
4 | Submit order to ERP |  | x |  | 0.5 | 30 | 30.5
5 | Schedule orders |  | x |  | 30 | 15 | 45
6 | Select carrier |  | x |  | 10 |  | 10
7 | Notify carrier |  | x |  | 0.5 | 60 | 60.5
8 | Carrier checks availability |  |  | x | 30 |  | 30
9 | Product picked | x |  |  | 60 | 10 | 70
10 | Product staged |  |  | x | 15 | 30 | 45
11 | Move trailer to DC |  |  | x | 45 | 15 | 60
12 | Load product | x |  |  | 75 | 10 | 85
13 | Transport product | x |  |  | 210 | 30 | 240
14 | Customer signs POD |  | x |  | 1 |  | 1
|  |  |  | Subtotals: | 486 | 200 | 686
| Cycle Time Units: | minutes
| TOTAL Cycle Time: | 686
| TOTAL VA Work Time: | 354
| % of Total Time: | 51.6%
NOTE: The following template contains SAMPLE data. Please populate the data in the template according to your project needs.

## Solution Selection Matrix
Solution Selection Matrix
Index
| Financial Impact | Ease of Implementation | Resources | Sigma Impact
Solution # | 10 | 8 | 4 | 5 | Score
1 | 5 | 7 | 8 | 1 | 143
2 | 2 | 4 | 7 | 9 | 125
3 | 3 | 2 | 1 | 4 | 70
4 | 4 | 6 | 7 | 6 | 146
5 | 3 | 3 | 3 | 4 | 86
Priority of Criteria | 1 Lowest 10 Highest
Effect of Solution on Criteria | 1 Least 10 Highest
Solution Selected:
Cost/Benefit Analysis:
DIRECTIONS: The template contains SAMPLE data.
1. Please populate your own criteria (row 3) according to your particular project needs.
2. Change the 'priority of criteria for each impact' (row 4).
3. Fill in the 'effect of the solution on the criteria' (the grey cells in the table) .

## FMEA
Failure Modes and Effects Analysis (FMEA)
Index
Process Name: |  |  | Prepared By: |  |  | Page: | __ of __
Responsible: |  |  | FMEA Date: |  |  | Rev:
Process | [9 empty] | Actions |  |  | Results
Process Step | Controllable/ Uncontrollable | Potential Failure Mode | Potential Effects of Failure | Severity | Potential Cause(s) of Failure | Occurrence | Current Controls | Detection | Initial Risk Priority Number | Recommended Action | Responsibility and Target Completion Date | Action Taken | Severity | Occurrence | Detection | Risk Priority Number
Text | C/U | Text | Text |  | Text |  | Text |  | 0 | Text | Text | Text |  |  |  | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
FMEA Standardized Ratings
RATING | DEGREE OF SEVERITY |  | LIKELIHOOD OF OCCURRENCE |  | ABILITY TO DETECT
1 | Customer will not notice the adverse effect or it is insignificant |  | Likelihood of occurrence is remote |  | Sure that the potential failure will be found or prevented before reaching the next customer
2 | Customer will probably experience slight annoyance |  | Low failure rate with supporting documentation |  | Almost certain that the potential failure will be found or prevented before reaching the next customer
3 | Customer will experience annoyance due to the slight degradation of performance |  | Low failure rate without supporting documentation |  | Low likelihood that the potential failure will reach the next customer undetected
4 | Customer dissatisfaction due to reduced performance |  | Occasional failures |  | Controls may detect or prevent the potential failure from reaching the next customer
5 | Customer is made uncomfortable or their productivity is reduced by the continued degradation of the effect |  | Relatively moderate failure rate with supporting documentation |  | Moderate likelihood that the potential failure will reach the next customer
6 | Warranty repair or significant manufacturing or assembly complaint |  | Moderate failure rate without supporting documentation |  | Controls are unlikely to detect or prevent the potential failure from reaching the next customer
7 | High degree of customer dissatisfaction due to component failure without complete loss of function. Productivity impacted by high scrap or rework levels |  | Relatively high failure rate with supporting documentation |  | Poor likelihood that the potential failure will be detected or prevented before reaching the next customer
8 | Very high degree of dissatisfaction due to the loss of function without a negative impact on safety or governmental regulations |  | High failure rate without supporting documentation |  | Very poor likelihood that the potential failure will be detected or prevented before reaching the next customer
9 | Customer endangered due to the adverse effect on safe system performance with warning before failure or violation of governmental regulations |  | Failure is almost certain based on warranty data or significant testing |  | Current controls probably will not even detect the potential failure
10 | Customer endangered due to the adverse effect on safe system performance without warning before failure or violation of governmental regulations |  | Assured of failure based on warranty data or significant testing |  | Absolute certainty that the current controls will not detect the potential failure
DIRECTIONS: Please refer to the FMEA Standardardized Ratings below for guidelines on how to conduct the FMEA.

## Control Plan
Control Plan
Index
Process Control System | [5 empty] | Date:
Process Description: | Process Customer: |  | CTQs: |  | Output/ Process Indicators:
Plan/Do | Check Process |  |  |  | Act/Fix Problem
Show Process Flow Chart Below | Key input, process or output measures | Standard/Specification |  | Method for sampling/recording data | Immediate control/fix | Procedure for improvement
Documentation | Monitoring |  |  |  | Reaction Plan

## Change Sustainability Model
Change Sustainability Model
Index
Project Name: |  | Date:
Describe specifically the change that will result from this project:
Change Area | WHAT structural change is needed? | HOW will the change be implemented? | WHO is needed to support this change? (list stakeholders and/or functions)
1. Attitudes, Believes and Mindsets
2. Knowledge, Skills and Abilities
3. Leadership and Management – what to start doing, stop doing or do differently?
4. Rewards and Incentives
5. Roles & Responsibilities
6. Organizational Structure – new team or reporting structures needed?
7. Work Processes – any additional up or downstream processes affected?
8. Policies and Procedures – new rules and/or regulations needed?
9. Performance Metrics – what metrics should be measure and tracked for long term success?
10. Information systems - any manual or electronic info systems needed for long term success?